## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Group 2 | 2026-02-18 | Cancellation rate calculation incorrect due to inconsistent statuts | Sprint 3 | Niyati Bansal | Logical | Converted appointment_status column to lowercase before filtering cancelled records. | 2026-02-18 | Closed | Verified manually after fix
2 | Group 2 | 2026-02-19 | Monthly trend chart missing data ue to incorrect date parsing | Sprint 3 | Priyanshi Kunte | Maintainability | Applied proper datetime conversion using pd.to_datetime() with error handling | 2026-02-19 | Closed | All months now visible
3 | Group 2 | 2026-02-20 | Department names not displayed correctly due to incorrect merge keys. | Sprint 3 | Eekshita Maram | Logical | Corrected foreign key mapping between room, roomrecords, and department tables. | 2026-02-20 | Closed | Department demand chart validated.
4 | Group 2 | 2026-02-21 | Completion rate graph appeared flat due to wide Y-axis scaling | Sprint 3 | Sheela Priyadharshini | User Interface | Adjusted Y-axis range dynamically to reflect small variations | 2026-02-21 | Closed | Graph now clearly readable.
5 | Group 2 | 2026-02-22 | Global filters were not consistently applied across multiple dashboard pages. | Sprint 3 | Mangali Meghana | Maintainability | Implemented consistent session state handling across pages. | 2026-02-23 | Closed | Filters synchronized successfully.
6 | Group 2 | 2026-02-22 | KPI cards not updating dynamically when filters were applied. | Sprint 3 | Divya Jaiswal | Logical | Modified KPI calculation logic to use filtered dataset instead of full dataset. | 2026-02-23 | Closed | KPIs now reflect selected filters.
7 | Group 2 | 2026-02-23 | Duplicate pateint records affecting admission count. | Sprint 3 | Rounak Kumar Manjhi | Maintainability | Used .drop_duplicated() and .nunique() for accurate counting. | 2026-02-23 | Closed | Admission count validated against dataset
8 | Group 2 | 2026-02-24 | Slow dashboard loading due to repeated data reading from Excel. | Sprint 3 | Kannan S | User Interface | Implemented @st.cache_data decorator to cache dataset loading. | 2026-02-24 | Closed | Performance improved significantly.